## ProjectTeam
Name | GitHub Alias
Sandro Luder | ludes2
Patrick Wyss | wyssp8
Joel Frutiger | JoelFrutiger
Claudio Polo | poloc1
Martin Kieliger | kielm1
André Pitta | a2pi

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Emergency Button | User can press a emergency button in the main view, which calls the emergency contact defined in the settings. | medium | 10 |  |  | waiting
2 | Excercises | User can view daily exsercises and can confirm these after done and can choose his calm-down excercises | high | 30 |  |  | waiting
3 | Diary | User can enter his current state of mind every day and is able to communicate his feelings using the diary | high | 30 |  |  | waiting
4 | Contacts | User can save contacts which can be used in settings | medium | 30 |  |  | waiting
5 | Settings | Select a Contact, which will be called when clicking the Emergency Button | medium | 15 |  |  | waiting
6 | Mainview | User can view the most recent diary entry and a random excercise. | low | 20 |  |  | waiting
7 | Login | User can register and login, data is stored in the database of the webserver | high | 45 |  |  | waiting
180

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Diary | Implement Diary view | Diary | Martin | Sandro | medium | 7 | x | 0 | done
1.2 | 1 | Settings | Set the contact for the emergency button. Three contact with priority, so if the first person do not answer, the second will bel called, and so the third. Account setting (change user). | button, contact | André | Martin | high | 7 | x | 7 | done
1.3 | 1 | Contact | implement the contacts | Model | Sandro | Claudio | high | 7 | x | 12 | done
1.4 | 1 | NavigationView | Implement the Navigation View and Presenter | NavigationView, NavigationPresenter | Joel | Patrick | high | 2 | x | 1 | done
1.5 | 1 | Exercises ExercisesView | Model of the classes and interfaces | Exersises model, classes, attributes, methodes | Patrick | Joel | high | 7 | x | 7 | done
1.6 | 1 | Emergency Button | Design the Emergency Button View | EmergencyView | Joel | André | medium | 5 | x | 5 | done
2017-07-01 | 1 | Login View | Design the Login View | LoginView | Claudio | Joel | high | 7 | x | 7 | done
1.8 | 1 | Logging | Add Logging functionality |  | Joel | Patrick | low | 1 | x | 1 | done
| 2 | Database Connection | Create ER Diagramm |  | all |  |  | 4 | x | 3 | done
| 2 | Database Connection | Create Database and connect using JDBC / Hibernate. |  | Patrick |  |  | 10 | x | 15 | done
| 2 | Daily Exercise | Add daily Exercise to mainview | MainView | Joel |  |  | 3 | x | 4 | done
| 2 | Latest Diary Entry | Add latest diary entry to main view | MainView | Joel |  |  | 3 | x | 2 | done
| 2 | State Pattern Implementation | Implement state pattern to main View |  | Joel |  |  | 8 | x | 8 | done
| 2 | Contacts functionality | Contacts can be deleted, added and edited. | Contact | Sandro |  |  | 14 | x | 14 | in progress (delete not done)
| 2 | Diary | Funktionalität implementieren |  | Martin |  |  | 14 | x | 14 | done
| 2 | Login | Implement login functionality and basic security, store session. |  | Claudio / Patrick |  |  | 10 | x | 11 | done
| 2 | Registration View | Design the registration View |  | Claudio |  |  | 4 | x | 4 | done
| 2 | Excercises | Generate Diary entry on exercise completed, split Excercises into daily and calm-down exercises. |  | Patrick |  |  | 4 | x | 2 | in progress (Generate Dairy Entrys not done)
| 2 | NavigationView | Icons / Design |  | André |  |  | 4 | x | 4 | done
| 2 | Settings | Improve functionality / add model |  | André |  |  | 10 | x | 8 | in progress (warten auf DB)
| 3 | Refactor code | Review all code and refactor if needed |  | all
| 3 | Unit tests | Write unit tests for the most important methods |  | all
| 3 | Contacts functionality | Delete contacts |  | done
| 3 | Exercises | Generate Diary entry on exercise completed |  | Patrick

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180